## Sheet1
Party Planner App
Members: | Julie Loi, Kevin Orellana, Quyen Wichers, Shubhu Shahade
Task | Description | Priority | Member | Status | Start Date | Complete Date | Comments
UI: Registration page | Prototype and Build the page | 4 | Julie Loi | Completed | 2021-02-26 | 2021-03-09 | Created Login Page UI, go to dashboard if logged in (3/24/21)
UI: Login page | Prototype and Build the UI page | 4 | Julie Loi | Completed | 2021-02-26 | 2021-03-09 | Created Sign Up Page UI
Firebase: Connect app to database | Setup Firebase, and connect to app | 4 | Kevin Orellana | Completed | 2021-03-03
DB: Design schema. | Design Objects and DB tables. Users, Event | 4 | Quyen Wichers | Completed | 2021-03-02 | 2021-03-09 | Basic design here https://app.diagrams.net/#G1iiefjp5vaxDWfqX7FP7G2EjMA9ODPcJu Will update if we have more feature
UI: Dashboard | Prototype and Build Dashboard | 4 | Julie Loi | Completed | 2021-03-11 | 2021-03-12 | Created Home Page UI
Firebase: Set up Authentication | Configure user authentication on Firebase console | 4 | Kevin Orellana | Completed | 2021-03-04
Validation: Registration Activity | Validate user input and save them in database. Check if email is registered | 4 | Quyen Wichers | Completed | 2021-03-11 | 2021-03-12
UI: Password forgot and reset page | Reset password upon forgetting previous password | 4 | Shubhu Shahade | Completed | 2021-04-21 | 2021-04-21
Validation: Login Activity | Check user inputs and alert the errors before submit | 4 | Julie Loi | Completed | 2021-03-11 | 2021-03-13 | Added red textbox for error and error message placement (appears and disappears given errors)
Firebase: Logout | Need a logout function and it should route to log in page | 4 | Kevin Orellana | Completed | 2021-03-11 | 2021-03-11 | Function is completed, Wait for logout UI to be implemented
UI: Party Page, Create/Edit Party, etc | Prototype Party Home Page and Related Pages (Create, Edit, View, etc) | 4 | Julie Loi | Completed | 2021-03-13 | 2021-03-16 | Created Party Page (from Home Screen) and relevant pages in Adobe XD: https://xd.adobe.com/view/0f1d2c02-0f7e-4d6b-bfea-58404bdd91e7-5a4e/
UI: Party Page Creation | Create Party Page in Android | 4 | Julie Loi | Completed | 2021-03-16 | 2021-03-18 | Created UI (Toolbar, TabLaout, Fragment Connection)
Firebase: Users | fetch User object after sign in | 4 | Kevin Orellana | Completed | 2021-03-11
UI: Navigation | Navigation tab display user info and logout button | 4 | Julie Loi | Completed | 2021-03-11 | 2021-03-15
DB: Design Invitation Objects | Store information about who invited, party type, isAccepted ...., partyID | 4 | Quyen Wichers | Completed | 2021-04-11 | 2021-04-12 | Decided only invited register users for now
Firebase: Parties | Setup add, get all methods | 4 | Quyen Wichers | Completed | 2021-03-19 | 2021-03-25 | Done with createParty and getParties functions.
UI: Added Logo to App (in Home Screen) | Changed basic app icon to the party planner logo | 4 | Julie Loi | Completed | 2021-03-23 | 2021-03-23
UI: Create Task Page | Create the Task Creation Page | 4 | Julie Loi | Completed | 2021-03-23 | 2021-04-12 | Created Basic Task List Page and Create Task Page; added spinner (drop-down), added subtask recyclerview and onClick for pending/complete status
UI: Party Fragment RecyclerView | Add recyclerviews to fragment | 4 | Julie Loi | Completed | 2021-03-23 | 2021-03-25 | Only needs to pass data to fragments from activity with party information. ------ I fix the data fragment problem already. So we can close this task -Quyen
Model: Task, Subtask | Created Java classes for the two models | 4 | Julie Loi | Completed | 2021-03-25 | 2021-03-25
UI: Task List (Create Task List) | Create UI with RecyclerView for list of tasks | 4 | Julie Loi | Completed | 2021-03-25 | 2021-03-25 | Only needs to pass data to activity with task list information
UI: Party Detail, Edit Party | Detail for a single party | 4 | Julie Loi | Completed | 2021-03-25 | 2021-04-02 | UI basics for edit party only
UI: Task Detail, Edit Task | Detail for a single task | 4 | Julie Loi | Completed | 2021-03-25 | 2021-04-02 | Subtask on hold, UI basics for edit task only
UI: Dashboard - Side Bar (log out button) | A sidebar appears when you press the user icon on the dashboard | 4 | Julie Loi | Completed | 2021-03-26 | 2021-03-26 | Still needs to show display name and add actions for profile and about
UI: Guest List (Part of Create Party function) | List of guests to invite | 4 | Julie Loi | Completed | 2021-03-26 | 2021-04-29 | Just needs to get list of users from backend and save it to the party
UI: Invitations | Dashboard mail icon to activity (recyclerview) | 4 | Julie Loi | Completed | 2021-03-29 | 2021-03-30 | Needs to get data and show though
UI: Invitation Detail | Detail for a single invitation | 4 | Julie Loi | Completed | 2021-03-29 | 2021-03-30 | Needs to get data and show though
Validation: Create Party Page | Validate User Input On Create Party View | 4 | Kevin Orellana | Completed | 2021-03-24
Bug: NO party breaks app | p.getParties() fails in Party Activity (~line 45) for new user | 4 | Quyen Wichers | Completed | 2021-04-11 | 2021-04-12 | Fixing
Bug: Party Activity need to reload | After creating party, new party doens't not show on the party list | 4 | Kevin Orellana | Completed | 2021-04-21 | 2021-04-21
Email or send text to users who get invited to the party | The party will add the friends from his list or enter email if that person isn't on the list | 4 | Shubhu Shahade | Completed | 2021-05-01 | 2021-05-02 | May need function to search for user email or phone number
UI: Contact List | Create Contact List, Contact Dialog | 4 | Julie Loi | Completed | 2021-04-12 | 2021-04-20 | Created recycler view and contact detail pop up dialog
UI: Budget List | Create Budget List | 4 | Julie Loi | Completed | 2021-04-12 | 2021-04-20 | Created Budget model and budget list recyclerview
Firebase: Users | Get all register users email or info for invitation | 4 | Quyen Wichers | Completed | 2021-04-18 | 2021-04-21
Firebase: AssociateUsers | AssociateUser object has referencing id of Authentication database user object. This will hold extra information of registered users | 4 | Quyen Wichers | Completed | 2021-03-12 | 2021-04-12
UI Service: Pass subtasks to parent views | Pass the subtasks, to the Create Tasks view and then to Create Party view | 4 | Kevin Orelalna | Completed | 2021-04-15 | 2021-04-20
UI:Add Guest List to Create Party | Show all users in db and use checkboxes to mark who gets an invite | 4 | Julie Loi | Completed | 2021-04-15 | 2021-04-19 | Only needs to get user list info and send checked guests as well
Firebase: Save task/subtask to the firestore DB | Save task/subtask information to the database | 4 | Kevin Orellana | Completed | 2021-04-15 | 2021-04-22
Backend: UserController getAllUsers | Make UserController.getAllUsers synchronous so GuestList can pull from it | 4 | Quyen Wichers | Completed | 2021-04-11 | 2021-04-14
Firebase: Invitation | Set up invitation in firebase | 4 | Quyen Wichers | Completed | 2021-05-03 | 2021-05-05 | Need to display the invitation to invitation list and have accept
Firebase: Party Detail- Guest List | Should have it where party id as reference id of guests collection | 4 | Quyen Wichers | Completed | 2021-05-02 | 2021-05-03
Backend: Guest list | The data from firebase need to be sync | 4 | Quyen Wichers | Completed | 2021-05-02 | 2021-05-03
Send Guest list back to the Create Party Activity | Send guest data back from the invite guest list page when creating a party | 4 | Quyen Wichers | Completed | 2021-04-29 | 2021-05-02
Save Task inside the Parties collection in Firestore | Save tasks and subtask in firestore | 4 | Kevin Orellana | Completed | 2021-04-26 | 2021-05-04
Fixed RecyclerView Issue in Task Detail | Fixed scrolling issue in recyclerview for task detail | 4 | Kevin Orellana | Completed | 2021-04-26 | 2021-04-29
Bug: Create Guest List opened several activities |  | 4 | Julie Loi | Completed | 2021-04-29 | 2021-05-02
UI: Guest List (Party Detail) | Shows list of invited guests to a party | 4 | Julie Loi | Completed | 2021-04-29 | 2021-05-02
UI: Task List (Party Detail) | Shows list of tasks associated to a party | 4 | Julie Loi | Completed | 2021-04-29 | 2021-05-02
UI: Task Detail (Dynamic) | Subtask changes are dynamically updated on task detail | 4 | Julie Loi | Completed | 2021-04-29 | 2021-05-02
Invitation Details / List - Finishing UI | waiting to be able to get party from database based on party id | 4 | Julie Loi | Completed | 2021-05-04 | 2021-05-06
Get Party from firebase | Get party from database based on party id | 4 | Quyen Wichers | Completed | 2021-05-04 | 2021-05-05
Firebase: forgot password | Setting up firebase to send email link for new password | 4 | Shubhu Shahade | Completed | 2021-04-25 | 2021-04-26
Forgot password activity | Code for forgot password activity | 4 | Shubhu Shahade | Completed | 2021-04-26 | 2021-04-26
GoogleAPI: Integrate Google Places API | Integrated on Create Party Activity | 4 | Kevin Orellana | Completed | 2021-03-24 | 2021-05-06
Allow user to mark a subtask as completed | Change the subtask object every time the user presses on the checkbox | 4 | Kevin Orellana | Completed | 2021-04-19 | 2021-04-26
Create Dialog to allow user to create a new subtask | Create Dialog to allow user to create a new subtask | 4 | Kevin Orellana | Completed | 2021-04-19 | 2021-04-26
Save Task Status to database | Save the task status as an integer in firestore | 4 | Kevin Orellana | Completed | 2021-05-04 | 2021-05-06 | Changed the STATUS from enum to IntDef type.
Set up Contacts Activity | Gets all users from contacts | 4 | Julie Loi | Completed | 2021-05-06 | 2021-05-06 | Reused Quyen's getAllGuests method for guest list, but for users in the contact activity
UI: Budget Details | Create Basic Budget Details Activity | 4 | Julie Loi | Completed | 2021-05-06 | 2021-05-06 | Removed Payment feature for now
Bug: reset password email not being sent by Firebase |  | 4 | Shubhu Shahade | Completed | 2021-05-06 | 2021-05-06
UI: Login activity | Login activity updated for forgot password | 4 | Shubhu Shahade | Completed | 2021-05-06 | 2021-05-06
UI: Guest invitation email |  | 4 | Shubhu Shahade | Completed | 2021-05-06 | 2021-05-09
UI: Event Page | Create and complete Event Page | 4 | Julie Loi | Completed | 2021-05-07 | 2021-05-09
Update Tasks | Make task list and party update when the subtasks are completed/added | 4 | Kevin Orellana | Completed | 2021-05-06 | 2021-05-12
Email message and subject | Wrote generic template email message and subject for party invitation | 4 | Shubhu Shahade | Completed | 2021-05-06 | 2021-05-12
Clean Project | Clean up code in project | 4 | Julie Loi | Completed | 2021-05-12 | 2021-05-14
Update Database when user changes a party | When a user updates a party update it to the database and pull the changes | 4 | Kevin Orellana | Completed | 2021-05-01 | 2021-05-11

## Utils (hidden)
Priority | Status | Member | All | Julie Loi | Kevin Orellana | Quyen Wichers | Shubhu Shahade
1 | Waiting
2 | Not Started
3 | In Progress
4 | Completed